## Overview
Hospital Preparedness Program (HPP) Health Care Coalition (HCC) Readiness Plan Template Overview
Purpose | You may use this readiness plan template to document how you will carry out activities and meet requirements for upcoming projects and acitivities throughout the course of the 5-year budget period (BP). The Office of Health Care Readiness (OHCR) is providing this work plan and budget template as an optional resource.
Notice of Funding Opportunity (NOFO) Instructions | You must submit a detailed fiscal year (FY) 2024 readiness plan in the first BP. Priorities: In this readiness plan, your HCC must describe top strategic priorities of your HCC(s) for each BP. Your HCC(s) should collaborate with you as they develop their top strategic priorities so that their Readiness Plan and the Strategic Plan for FY 2024–2028 are aligned and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments. Implementation Planning: Describe how your HCC(s) will implement activities. This should include your HCC(s)’s method for: • Developing the required materials identified in this NOFO, including approach, timelines, and expected milestones. Note: You and your HCC(s) must adhere to the submission deadlines specified in the timing and deadlines table. • Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement. • Engaging community partners. • Facilitating continuous improvement from the previous BP. HCC Growth and Development: Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • Manage and improve administrative and financial functions. • Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Readiness Plan Template Content
Tab | Description
Activity Requirements | A reference table of activity requirements for the FY 2024–2028 HPP NOFO with submission instructions and timeline and administrative oversight activities.
HCC Priorities | Readiness Plan component
HCC Development | Readiness Plan component
Establish Governance | Readiness Plan component
Assess Readiness | Readiness Plan component
Plan and Implement | Readiness Plan component
Exercise and Improve | Readiness Plan component
Training and Exercise (T&E) Plan Instructions | T&E Plan component
T&E Plan | T&E Plan component
Reference Table
HPP NOFO Outcomes | Description
Establish and act on multi-year priorities. | Outcomes include: • Health care delivery system readiness to respond to a shifting threat landscape and community needs over multiple years. • Continuous programmatic and administrative improvement on multi-year priorities.
Enhance and sustain HCCs. | Outcomes include: • HCC governance, management, and operations that reflect community partnerships.
Coordination. | Outcomes include: • Coordinated planning and decision-making among health care delivery system partners. • State, local, tribal, and territorial agencies, HCCs, and other partners provide integrated health care response incident management (Emergency Support Function #8 [ESF-8] – Public Health and Medical Services).
Continuity of health care service delivery. | Outcomes include: • A resilient health care workforce able to safely meet response and recovery demands. • Suficient space, systems, staff, and resources to support patient movement and patient care delivery during response and recovery. Note: As used in the HPP NOFO, “health care workforce” does not refer only to clinical providers, but also includes all those who support the functioning of health care during disasters and emergencies.
HPP NOFO Core Functions | Description
Assessment and risk mitigation. | Anticipate challenges and mitigate risks to support decision-making that meets community or jurisdiction health care needs during a disaster or emergency.
Information sharing. | Collect and share near real-time information to provide multidirectional health care situational awareness during an emergency or disaster.
Specialty care planning and coordination. | Incorporate necessary expertise to support health care readiness planning, disaster and incident management, including for specialty care delivery, and/or to address specific hazards or events.
Respond. | Coordinate and support the implementation of plans, policies, and procedures among recipients, HCCs, HCC members, and their partners to address patient care needs during an emergency or disaster.
Health care workforce support. | Equip, protect, and support the health care workforce by providing access to health care readiness resources, training, and exercises.
Resource management. | Facilitate resource management and planning among recipients, HCCs, HCC members, and their partners to mitigate shortfalls, maintain operations, and sustain delivery of patient care services during an emergency or disaster.
Training, exercise, and evaluation. | Conduct trainings, exercises, and evaluations that incorporate input from assessments, plans, policies, and previous trainings and exercises to evaluate, validate, and improve readiness and response processes.
Continuity and recovery. | Support the improvement of processes and systems that promote continuity of health care operations and aid in recovery.
Organizational development. | Create and carry out strategies to sustain and grow HCCs and their partnerships.
End of worksheet

## Activity Requirements
FY 2024–2028 HPP NOFO Requirements
The following table is for your reference. Please refer to the HPP NOFO Timing and Deadlines table for activities 1-4 on p. 44-45 of the HPP NOFO. Refer to the Benchmarks table for Recipient and HCC benchmarks on p. 42 of the HPP NOFO.
Activities | Guidance
0. Administrative Oversight Activities | 0. Administrative Oversight – Guidance
0.1 Program Administration | Work with HCCs and pertinent partners to maintain program oversight throughout the period of performance. Please adhere to program requirements listed in the NOFO and the rules listed in 45 Code of Federal Regulations (CFR) Part 75.
0.2 Financial Administration | Develop and administer budgets that support submitted work plans and comply with the rules listed in 45 CFR Part 75, Uniform Administrative Requirements, Cost Principles, and Audit Requirements for U.S. Department of Health and Human Services (HHS) Awards throughout the period of performance.
Activities | Submission Instructions and Timeline | Responsible Owner
1. Establish Governance Activities | 1. Establish Governance – Submission Instructions and Timeline | 1. Establish Governance – Responsible Owner
1.1 HCC Governance Document | Submit by January 31, 2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
1.2 Jurisdiction Information | Submit by January 31, 2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
2. Assess Readiness Activities | 2. Assess Readiness – Submission Instructions and Timeline | 2. Assess Readiness – Responsible Owner
2.1 Risk Assessment (RA) Note: Previously known as Jurisdiction Risk Assessment (JRA) | Submit once every five years. If you submitted a JRA during the prior HPP FY 2019–2023 period of performance, you must submit the RA five years after that submission. | HPP recipient with input from HCCs
2.2 Hazard Vulnerability Assessment (HVA) | Submit by January 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.3 Readiness Assessment | Submit by January 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.4 Supply Chain Integrity Assessment | Review the current Supply Chain Integrity Assessment and submit updated material each BP. If you and your HCC(s) do not have a supply chain assessment, submit this by December 31, 2026 (BP3). Review and submit updated material each BP from BP4–BP5. | HCC in coordination with HPP recipient
2.5 Workforce Assessment | Submit by December 31, 2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
2.6 Cybersecurity Assessment | Due by June 30, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.7 Extended Downtime Health Care Delivery Impact Assessment | Due by June 30, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3. Plan and Implement Activities | 3. Plan and Implement – Submission Instructions and Timeline | 3. Plan and Implement – Responsible Owner
3.1 Strategic Plan for FY 2024–2028 | Due by March 31, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HPP recipient with input from HCCs
3.2 Readiness Plan | Due by March 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.2.1 Training and Exercise Plan | Due by March 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.3 Response Plan Activities | 3.3 Response Plan – Submission Instructions and Timeline | 3.3 Response Plan – Responsible Owner
3.3.1 Information-Sharing Plan | Review the current information-sharing plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have an information-sharing plan, submit this by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.2 Resource Management Plan | Review the current resource management plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a resource management plan, submit this by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.3 Workforce Readiness/Resilience Plan | Due by December 31, 2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.4 Medical Surge Support Plan | Review the current medical surge support plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a medical surge support plan, submit by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.5 Patient Movement Plan | You and your HCC(s) must define the submission deadline for the Patient Movement Plan when you and your HCC(s) develop your Readiness Plan. Once submitted, review each BP and submit updated material as needed. | HPP recipient with input from HCCs
3.3.6 Allocation of Scarce Resources Plan | You and your HCC(s) must define the submission deadline for the Allocation of Scarce Resources Plan when you develop your Readiness Plan. Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4 Continuity and Recovery Plan Activities | 3.4 Continuity and Recovery Plan – Submission Instructions and Timeline | 3.4 Continuity and Recovery Plan – Responsible Owner
3.4.1 Continuity of Operations Plan (COOP) | Review the current COOP each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a COOP, complete this by June 30, 2025 (BP1). Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.2 Cybersecurity Support Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.3 Extended Downtime Support Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.4 Recovery Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
4. Exercise and Improve Activities [1] | 4. Exercise and Improve – Submission Instructions and Timeline | 4. Exercise and Improve – Responsible Owner
4.1 Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP. | HCC with HPP recipient support
4.2 Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan. | HPP recipient with HCC participation
4.3 Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs. | HCC with HPP recipient support
4.4 Cybersecurity Exercise | Complete once by June 30, 2027 (BP3). | HCC with HPP recipient support
4.5 Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5. | HCC with HPP recipient support
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance. | HPP recipient with HCC participation
4.7 Statewide Exercise | Complete once in the five-year period of performance. | HPP recipient with HCC participation
[1] Please refer to Exercise and Improve section of the HPP NOFO for a full list of requirements for this section.
Please note that certain compliance requirements, like the requirement to conduct at least one exercise that address the needs of at-risk individuals and communities most impacted by disasters, are not listed in this table.
End of Worksheet

## Readiness Plan Overview (hidden)
Readiness Plan Overview
HCC Priorities | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024-2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Implementation Planning | On the activity tabs, develop the required materials identified in the NOFO, including approach, timelines, and expected milestones. • adhere to the submission deadlines specified in the activity requirements tab •
• Use your readiness assessment Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement.
• Engaging community partners.
• Facilitating continuous improvement from the previous BP.
HCC Development
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • (HCC) Manage and improve administrative and financial functions. • (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
• (HCC) Manage and improve administrative and financial functions.
• (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).

## HCC Priorities
Readiness Plan – Priorities
Description | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024–2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Priority | HCC Priorities | Description and Approach
Rank of Priority | Select your priority area from highest priority to lowest (minimum 5). | Describe your approach to address your priority needs including: 1. Primary reason(s) for priority (e.g., critical gap finding, strategic plan alignment, etc.) 2. Briefly summarize how the HCC will approach the priority (e.g., The HCC will complete the patient movement plan in year 1 and perform a detailed gap analysis regarding needs in the region).
Example | 1. Establish governance | 1. Our HCC has determined that financial and independent growth is the best way to develop a sustainable coalition. 2. In year one, the HCC will contract with financial and marketing specialists to determine a path forward to 501c3 incorporation and income sustainability.
1 | 2.2 Hazard Vulnerability Assessment (HVA) | 1. Our HCC has determined that our HVA is an important action item as it helps us determine gaps and priorities for our members and community 2. Annually, the BBHCC will conduct an HVA with members and stakeholders.
2 | 2.6 Cybersecurity Assessment | 1. Cybersecurity is a vulnerability and concerns identified by our members. 2. The Cybersecurity Assessment will help the Coalition put the concerns of our members to paper and help identify gaps and opportunities for improvement
3 | 2.7 Extended Downtime Health Care Delivery Impact Assessment | 1. Extended Downtimeis a vulnerability and concern identified by our members. 2. The Extended Downtime Assessment will help the Coalition put the concerns of our members to paper and help identify gaps and opportunities for improvement
4 | 3.4.2 Cybersecurity Support Plan | 1. Cybersecurity is a vulnerability and concern identified by our members. 2. The Cybersecurity Plan be based off the gaps identified in the Cybersecurity assessment.
5 | 3.4.3 Extended Downtime Support Plan | 1. Extended Downtimeis a vulnerability and concern identified by our members. 2. The Extended Downtime plan will be based off the gaps identified in the assessment.
6 | 3.4.1 Continuity of Operations Plan (COOP) | 1. The Coalition COOP has not been updated recently. 2. The current COOP will be analyzed and updated and reviewed by our staff.
7 | 4.1 Medical Response and Surge Exercise (MRSE) | 1. MRSE is an annual requirement that prepares and trains our members for MCI 2. The HCC will complete an annual MRSE using the MRSE planning and exercise tool. BBHCC tries to work with local agencies to combine MRSE with any other exercises if available.
8 | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | 1. BBHCC is working to develop an exercise on wildfires espcially for local SNF, LTC, ALF and other facilitites.
9 | 0. Administrative Oversight | 1. BBHC will ensure both program and finace adminsitration meets grant requirements.
10 | 1. Establish governance | 1. BBHCC as determined that financial and independent growth is the best way to develop a sustainable coalition. 2. BBHCC will continue to evaluate ways to support financial stength. This includes further cost sharing with other HCC's.
End of Worksheet
Select One
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise
Other

## HCC Development
Readiness Plan – HCC Growth & Development
Activities listed below must support the administrative management and monitoring of the cooperative agreement.
Instructions and reminders:
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: 1) Manage and improve administrative and financial functions. 2) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Please provide at least one activity for program administration, financial administration, and strategic communication.
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This must be the role title of the personnel responsible for the administration or management activty and can speak to the intended output.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Item Number | HCC Development Activity | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date
Example | Sub-recipient Monitoring and Management | In coordination with the Program Director, the HPP Finance team will perform site visits to each sub-recipient to audit finance and program activities in Budget Period 1. | Site visit report includes financial audit for each sub-recipient. | Finance Director | 2025-06-30
1 | HCC Administration | In coordination with our members, BBHCC will conduct a strategic planning workshop | Complete a 2025-2029 strategic plan for BBHCC to help guide future focus and activities | HCC Staff | 2026-10-30
2 | Financial Administration | Continue to provide monthly and quarterly finance updates to Recipient and Board of Directors | Full transparency of funding expending | HCC Staff | 2026-06-30
3 | Strategic Communication | Develop a newsletter to send out quarterly | produce a quarterly newsletter to help keep members informaed | HCC Staff | 2026-06-30
4 | Strategic Communication | Continue with annual comunication drills | Ensure that members and partners are prepared to initiate communication should there be an emergency | HCC Staff | 2026-06-30
5 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
6 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
7 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
8 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
9 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
10 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
11 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
12 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
13 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
14 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
15 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
16 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
17 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
18 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
19 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
20 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
21 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
22 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
23 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
24 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
25 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
26 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
27 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
28 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
29 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
30 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
End of Worksheet
Select One
HCC Administration
Financial Administration
Strategic Communication

## Establish Governance
Readiness Plan – Implementation Planning: Establish Governance
Activities listed below must support establishing governance in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | HCC Governance Document | The BBHCC Executive Committee and necessary ARPC Staff will annually review the BBHCC Bylaws to ensure that all governance document checklist activities are met | Updated bylaws to include the Funding Structure | HCC Coordinator | 2025-12-15 | Organizational development | Enhance and sustain HCCs
2 | Jurisdiction Information | The jurisidicational information is complete. | Maintain jurisdictional information in compliance with APSR NOFO, will continue to provide updates | HCC Coordinator | 2025-12-15 | Organizational development | Enhance and sustain HCCs
3 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
4 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
5 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
6 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
7 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
8 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet

## Assess Readiness
Readiness Plan – Implementation Planning: Assess Readiness
Activities listed below must support assessing readiness in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Work Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Risk Assessment (RA) | Coordinate with PHEP recipient point of contact to complete a new RA to prepare for a disaster or emergency by providing and incorporating input from members (Hospitals, EM, Public Health, EMS). | Complete Risk Assessment | HCC Staff | 2025-12-25 | Assessment and risk mitigation | Establish and act upon multi-year priorities
2 | Hazard Vulnerability Assessment (HVA) | Survey annually BBHCC members/partners for HVA input. Share final HVA with members for review and final input. Use the HVA to help identify additional training and exercises. | Completed HVA | HCC Staff | 2025-12-25 | Assessment and risk mitigation | Continuity of health care service delivery
3 | Readiness Assessment | BBHCC Executive Committee will meet annually to conduct a readiness assessment and provide recommendations on priorities. The completed readiness assessment will be shared with members afterwards and they will be offered an opportunity for feedback | Completed Readiness Assessment | HCC Staff | 2025-12-15 | Assessment and risk mitigation | Establish and act upon multi-year priorities
4 | Supply Chain Integrity Assessment | BBHCC will adapt their most recent Supply Chain Integrity Assessment to complete this activity. BBHCC will collaborate with community partners and health care readiness partners, including manufacturers and distributors, to conduct this assessment. This assessment is complete when each of the following have been addressed: Resource Needs, Vulnerabilities, Current access and infrastructure, Impact on communities, and Mitigation Strategies | Completed Supply Chain Integrity Assessment | HCC Staff | 2025-12-15 | Assessment and risk mitigation | Continuity of health care service delivery
5 | Cybersecurity Assessment | BBHCC will work with the recipient, members, and community subject matter experts to conduct a cybersecurity assessment. This assessment will assess use of cybersecurity practices, describe community impact of a potential cyber incident on communities most impacted by disasters, and identify mitigation strategies. | Completed Cybersecurity Assessment | HCC Staff | 2026-06-30 | Assessment and risk mitigation | Establish and act upon multi-year priorities
6 | Extended Downtime Health Care Delivery Impact Assessment | BBHCC will complete an extended downtime health care delivery impact assessment of our immediate jurisdictional area. This assessment will identify the following for non-cyber extended downtime events: Impacted functions, community impact, and mitigation strategies. | Completed Extended Downtime Health Care Delivery Impact Assessment | HCC Staff | 2026-06-30 | Assessment and risk mitigation | Establish and act upon multi-year priorities
7 | Workforce Assessment | BBHCC will collaborate with members, community partners, and additional health care readiness partners to conduct a workforce assessment. This assessment will identify: • vulnerabilities, • the ability to provide specialty expertise, • ability to provide care to the communities within the jurisdiction, including communities most impacted by disasters • training needs • workforce safety and health resources • community impact • mitigation strategies | Completed Workforce Assessment | HCC Staff | 2026-12-15 | Health care workforce support | Establish and act upon multi-year priorities
8 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet

## Plan and Implement
Readiness Plan – Implementation Planning: Plan and Implement
Activities listed below must support planning and implementation in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Strategic Plan for FY 2024-2028 | BBHCC will participate in all strategic planning activities laid out by the Recipient in helping them formulate a state-wide Strategic Plan. | A state-wide strategic plan with input from all HCCs | HCC Staff | 2025-03-31 | Continuity and recovery | Enhance and sustain HCCs
2 | Strategic Plan for FY 2024-2028 | BBHCC will conduct its own Strategic Planning workshop in January 2025 during which it will ask its members for input on the goals, objectives, and future of the BBHCC | A Coalition specific Strategic Plan | HCC Staff | 2026-10-30 | Continuity and recovery | Enhance and sustain HCCs
3 | Readiness Plan | After conducting the readiness assessment, BBHCC will complete a readiness plan describing top strategic priorities for the HCCs for each BP. The draft will be completed by BBHCC staff and shared with the Executive board for review and approval and then be shared with members and partners for feedback. | A completed Readiness Plan (this document) | HCC Staff | 2025-12-15 | Organizational development | Establish and act upon multi-year priorities
4 | Training and Exercise Plan | BBHCC will develop a comprehensive training and exercise plan in conjunction with the Recipient and our members | A completed Training and Exercise Plan (last tab of this document) | HCC Staff | 2025-12-15 | Training, exercise, and evaluation | Establish and act upon multi-year priorities
5 | Response Plan: Information-Sharing Plan | BBHCC will review and update the current Information Sharing Plan | An updated Information-Sharing Plan | HCC Staff | 6/30/2025, annually afterwards | Information sharing | Coordination
6 | Response Plan: Resource Management Plan | BBHCC will review and update the current Resource Management Plan | An updated Resource Management Plan | HCC Staff | 6/30/2025, annually afterwards | Resource management | Coordination
7 | Response Plan: Workforce Readiness / Resilience Plan | BBHCC's Workforce Readiness/Resilience Plan will describe how we spport the healthcare workforce's access to resources that support workforce safety and resilience. The Training and Exercise Plan will show how the Coalition engages the health care workforce in trainings and exercises. The plan will address gaps identified in the workforce assessment | A completed Workforce Readiness/Resilience Plan | HCC Staff | 6/30/2027, updated annually after | Health care workforce support | Continuity of health care service delivery
8 | Response Plan: Medical Surge Support Plan | Review and update the current Pediatric, Burn, Infectious Disease/Special Pathogens, Radiation, and Chemical Annexes | An updated Medical Surge Support Plan | HCC Staff | 6/30/2025, annually afterwards | Specialty care planning and coordination | Continuity of health care service delivery
9 | Response Plan: Patient Movement Plan | Engaging with core partners,along with patient transport services and other transportation services, to coordinate patient movement and load balancing, BBHCC will complete a Patient Movement Plan. | A completed Patient Movement Plan | HCC Staff | 2028-06-30 | Specialty care planning and coordination | Coordination
10 | Response Plan: Allocation of Scarce Resources Plan | Using the current BBHCC Crisis Standards of Care Guidelines and Plans, BBHCC will develip and maintain an Allocation of Scarce Resources Plan. | A completed Allocation of Scarce Resources Plan | HCC Staff | 2028-06-30 | Resource management | Coordination
11 | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | BBHCC will review and update the current COOP plan | An updated Continuity of Operations Plan | HCC Staff | 6/30/2025, annually afterwards | Continuity and recovery | Continuity of health care service delivery
12 | Continuity and Recovery Plan: Cybersecurity Support Plan | Using the BBHCC Cybersecurity Assessment, BBHCC will prioritize implementation of high-impact cybersecurity practices and describe at a high-level the steps they intend to take to address these gap areas. For example, HCCs may identify “Basic Cybersecurity Training” as an HPH Sector-Specific CPG gap area to address. An intended next step may be updating their support plan to include high-level practices to address this goal (e.g., hosting cybersecurity trainings, identifying relevant technical assistance resources). | A completed Cybersecurity Support Plan | HCC Staff | 6/30/2027, annually afterwards | Continuity and recovery | Continuity of health care service delivery
13 | Continuity and Recovery Plan: Extended Downtime Support Plan | Using the BBHCC Cybersecurity Assessment and Extended Downtime Health Care Delivery Impact Assessment, BBHCC will address gaps including preventative actions to protect a coalition-wide system from downtime events and actions that BBHCC will take to prepare the healthc are delivery system to absorb patient care from impacted entities. The plan will also address the management and mitigation of disruptions to clinical or operational activities from a downtime event impacting the Big Bend region. | A completed Extended Downtime Support Plan | HCC Staff | 6/30/2027, annually afterwards | Continuity and recovery | Continuity of health care service delivery
14 | Continuity and Recovery Plan: Recovery Plan | Create and update a BBHCC Recovery Plan that will show integration with key partners, supporting the workforce, prioritizing of critical infrastructure recovery, addresses anticipated recovery needs for the community, and how to engage and support community partners to connect with recovery assistance programs. | A completed and updated Recovery Plan | HCC Staff | 6/30/2026, annually afterwards | Continuity and recovery | Continuity of health care service delivery
15 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet

## Exercise and Improve
Readiness Plan – Implementation Planning: Exercise and Improve
Activities listed below must support exercises and improvement in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Medical Response Surge Exercise (MRSE) | BBHCC will hold an annual MRSE during which will surge member hospitals according to the MRSE Exercise Reporting Tool. The Tool will be filled out using the MRSE manual, MRSE Evaluation Plan, and Recipient Review Guide with the help of our Clinical Advisor | An annual Medical Response Surge Exercise with member participation | HCC staff | 2026-05-13 | Training, exercise, and evaluation | 4.1 Medical Response and Surge Exercise (MRSE)
2 | Patient Movement Exercise | BBHCC will conduct a Patient Movement Exercise upon completion of its Patient Movement Plan | A completed Patient Movement Exercise | HCC staff | 2029-06-15 | Training, exercise, and evaluation | 4.2 Patient Movement Exercise
3 | Cybersecurity Exercise | BBHCC will conduct a Cybersecurity Exercise upon completion of its Cybersecurity Support Plan. An AAR will be developed and submitted. | A completed Cybersecurity Exercise and AAR | HCC staff | 2027-06-15 | Training, exercise, and evaluation | 4.4 Cybersecurity Exercise
4 | Non-Cyber Extended Downtime Exercise | BBHCC will conduct a Non-Cyber Extended Downtime Exercise upon completion of its Extended Downtime Support Plan | A completed Non-Cyber Extended Downtime Exercise | HCC staff | 2028-06-15 | Training, exercise, and evaluation | 4.5 Non-Cyber Extended Downtime Exercise
5 | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | In conjunction with the Recipient, BBHCC will participate in an exercise that addresses a jurisdictional priority defined in the Recipient and HCC Strategic Plan or Readiness Plan, an identified gap from our assessments, previous exercises or improvement plans, or one of our identified critical risks | A completed exercise addressing jurisdictional priorities or areas of improvement | HCC staff | 2027-05-30 | Training, exercise, and evaluation | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
6 | Statewide Exercise | In collaboration with the Recipient, the BBHCC will participate in a statewide exercise during which it will collaborate with health care readiness partners including Public Health, State Emergency Management, Other HCCs, and Additional Health Care Readiness Partners | A completed Statewide Exercise | HCC staff | 2028-05-30 | Training, exercise, and evaluation | 4.7 Statewide Exercise
7 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
8 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet

## T&E Plan Instructions
Hospital Preparedness Program (HPP) HCC T&E Plan Template Overview
Purpose | The Administration for Strategic Preparedness and Response (ASPR)’s OHCR developed a template for the T&E Plan to support you and your HCCs with completing activity requirements for the T&E Plan. Please refer to the FY 2024–2028 HPP NOFO for more information.
NOFO Instructions | Template content: The T&E Plan template contains a detailed table to organize a timeline of all planned and projected trainings and exercises for the FY 2024–2028 period of performance, beginning on July 1, 2024, and ending on June 30, 2029. An example is provided. Submission deadline and updates: The T&E Plan is due by March 31, 2025. You and your HCC(s) must provide information for trainings and exercises for all five BPs. You and your HCC(s) must make updates and submit a revised T&E Plan each BP from BP2–BP5. Please provide the date of your last update in the footer of the template. • Identify the type of exercise, which can be one of the following: • Seminar. • Workshop. • Tabletop exercise. • Drill. • Functional exercise. • Full-scale exercise. • Address communities most impacted by disasters (p. 14 of the HPP NOFO). • Include engagement with health care readiness partners, as appropriate (p. 13-15 of the HPP NOFO). • Describe how you and your HCC(s) will engage the health care workforce in trainings and exercises (p. 30 of the HPP NOFO). • Include, as appropriate, any trainings and exercises in the example list of topics (p. 89 of the HPP NOFO). Please note the following funding policies and limitations (p. 51 of the HPP NOFO): • You may not use funds to support standalone, single-facility exercises. • You may not spend HPP funds on training courses, exercises, and planning resources when similar offerings are available at no cost.
Your T&E Plan must, at a minimum, include the following required trainings and exercises:
Training/Exercise | Submission Instructions and Timeline
National Incident Management System (NIMS) training | Throughout the five-year period of performance.
Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP.
Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan.
Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs.
Cybersecurity Exercise | Complete once by June 30, 2027 (BP3).
Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5.
Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance.
Statewide Exercise | Complete once in the five-year period of performance.
If you decide to make this the Recipient T&E Plan template, recipients with large numbers of HCCs (e.g., CA) may have an issue with listing every HCC's annual MRSE.
In those situations, we can add a caveat to only list a MRSE in their plan if they have a significant role.
End of Worksheet

## T&E Plan
HPP HCC T&E Plan
HCC name: | BBHCC
Date of last update: | 2025-12-09
BP1
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2025-08-01 | Patient Movement Exercise | Full-scale exercise | Major flooding | Hospitals, LTC, EMS, EM, & HCCs | State MOCC, OEM, & DOT | FEMA Regional Response Plans | Joe Smith joesmith@gmail.com
2025-01-30 | FIT train the trainer | Training | Infectious respiratory | DOH & EMS | DOH | Training materials | etodak@arpc.org/clevings@arpc.org
2024-09-01 | ICS FORMS class | Training | ICS | HCC Members | TEEX | Training materials | etodak@arpc.org/clevings@arpc.org
2025-02-28 | TEEXPediatric Disaster Response | Training | Pediatrics | Hospitals, EMS, EM, DOH, Fire | TEEX | Training materials | etodak@arpc.org/clevings@arpc.org
2025-05-01 | Medical Response and Surge Exercise MRSE | Functional | Medical Surge | Hospitals, EMS, EM | DEM, ESF-8, Local EMS/Fire | MRSE Exercise Documents | etodak@arpc.org/clevings@arpc.org
2025-04-01 | Continuity of Operation Plan COOP workshop | Training | Downtime Procedures/Business Continuity | HCC Members | BOLDPlanning | Training documents | etodak@arpc.org/clevings@arpc.org
2025-04-01 | Wildfire training and tabletop | Exercise | TBD | all members | All-Clear | Exercise document & AAR | etodak@arpc.org/clevings@arpc.org
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
BP2
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2026-05-01 | Medical Response and Surge Exercise MRSE | Functional | Medical Surge | Hospitals, EMS, EM | DEM, ESF-8, Local EMS/Fire | MRSE Exercise Documents | etodak@arpc.org/clevings@arpc.org
2026-06-01 | CyberSecurity Exercise | TTX | Continuity of Operations | Hospitals, LTC, EMS, EM | CISA, DEM, FBI | BBHCC Cybersecurity Support Plan | etodak@arpc.org/clevings@arpc.org
2025-11-01 | MGT 314-Medical Preparedness and Response for Bombing Incidents | Training | Response Plans | HCC Members | TEEX | training materials | etodak@arpc.org/clevings@arpc.org
2026-05-01 | O305-All Hazards | Training | ICS-Response Plans | HCC Members | TBD | training materials | etodak@arpc.org/clevings@arpc.org
2026-04-01 | MGT-348 Preparing for Cyber Attacks and Incidents | Training | Cybesecurity | HCC Members | TEEX | Training | etodak@arpc.org/clevings@arpc.org
2026-set date not set | Water shortage tabletop | Exercise | Response Plans | HCC Members | TBD | Exercise AAR | etodak@arpc.org/clevings@arpc.org
2026-01-01 | 15 to 50 exercise | Exercise | Response Plans | Hospital | ESF 8, HCA Hospital | Exercise AAR | etodak@arpc.org/clevings@arpc.org
2025-04-26 | Regional shelter-in-place train-the-trainer | Training/Exercise | Hands on shelter-in-place training | HCC Members, whole community | R3 HCC Alliance, Northeast LEPC, Apalachee LEPC. | Training materials | clevings@arpc.org
BP3
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2027-05-01 | Medical Response and Surge Exercise MRSE | Functional | Medical Surge | Hospitals, EMS, EM | DEM, ESF-8, Local EMS/Fire | MRSE Exercise Documents | etodak@arpc.org/clevings@arpc.org
2027-05-01 | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | TTX | TBD | Hospitals, LTC, EMS, EM | State FDOH/ESF-8 | BBHCC HVA | etodak@arpc.org/clevings@arpc.org
2026-10-01 | MGT 319 | Training | POD | Hospitals, DEM, ESF-8, Fire Rescue, EMS, LTCs. ALFs | TEEX | Training materials | etodak@arpc.org/clevings@arpc.org
2026-12-01 | PER 211-Medical Management of CBRNE Events’ | Training | Response Plans | HCC Members | TEEX | training materials | etodak@arpc.org/clevings@arpc.org
2027-06-01 | Pathogens Exercise/workshop | Exercise | Response Plans | HCC Members | DOH, EM, EMS | Training & exercise AAR | etodak@arpc.org/clevings@arpc.org
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
BP4
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2028-05-01 | Medical Response and Surge Exercise MRSE | Functional | Medical Surge | Hospitals, EMS, EM | DEM, ESF-8, Local EMS/Fire | MRSE Exercise Documents | etodak@arpc.org/clevings@arpc.org
2028-05-01 | Non-Cyber Extended Downtime Exercise | TTX | Continuity of Operations/Business | Hospitals, LTC, EMS, EM | DEM, ESF-8, EMS | BBHCC Extended Downtime Support Plan | etodak@arpc.org/clevings@arpc.org
2028-05-01 | Statewide Exercise | TTX | TBD | Hospitals, LTC, EMS, EM | DEM, ESF-8, EMS | TBD | etodak@arpc.org/clevings@arpc.org
2028-04-01 | Workplace Violence Workshop | Training | WPV Prevention | Hospitals, LTCs. ALFs | N/A | Training materials | etodak@arpc.org/clevings@arpc.org
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
BP5
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2029-05-01 | Medical Response and Surge Exercise MRSE | Functional | Medical Surge | Hospitals, EMS, EM | DEM, ESF-8, Local EMS/Fire | MRSE Exercise Documents | etodak@arpc.org/clevings@arpc.org
2029-06-01 | Patient Movement Exercise | Functional and Full-Scale | Mass Casualty Incident | Hospitals, DEM, ESF-8, Fire Rescue, EMS | DEM, EMS/Fire, FDOH | Exercise Plan and Document | etodak@arpc.org/clevings@arpc.org
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
[mm/yyyy] | [name of the training or exercise] | [type of training or exercise] | [priority addressed by conducting the training or exercise] | [audience for the training or exercise] | [any partners needed to conduct the training or exercise] | [any relevant resources] | [name, email]
End of Worksheet

## Instructions (hidden)
ASPR HPP FY2019-2023 HCC Budget: Instructions
1) Proceed to the worksheet tab for each category that funding is requested
2) For each line item, fully complete the data fields for the entire row
3) For cells with a dropdown menu, please select the most appropiate response; do not enter custom text
4) For cells requesting a custom text, be clear and concise to ensure text limits are not exceeded
5) When entering detailed justification statements, be clear and concise to ensure text limits are not exceeded.
6) All dollar amounts to be funded by the program must be fully accounted for; this includes allocation breakdowns between capabilities as well as when cost share is being applied between programs (i.e. HPP vs. PHEP)
7) All line items must be associated with an appropiate HPP activity or multiple activities; failure to identify HPP activities may result in budget restrictions
8) All HPP activities identified in the HCC Budget must be accounted for in the HCC Work Plan; failure to account for HPP activities in the HCC Work Plan may result in budget restrictions

## Sheet1 (hidden)
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
0.3 Sub-recipient Monitoring and Management
0.4 Program Reporting
0.5 Performance Evaluation
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise

## Data Validation (hidden)
Data Validation
Administrative Oversight | 1. Establish Governance |  |  | 2. Assess Readiness |  |  | 3. Plan and Implement |  |  | 4. Exercise and Improve |  |  | Budget - Personnel |  | Budget - Personnel |  | Budget - Travel | Budget - Contractual |  | Budget - Indirect Costs | Budget - Match
Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select One | Select one | 0% | 0% | Select one | Select one | Select one | (Yes/No) | Select one
Program Administration | HCC Governance Document | Assessment and risk mitigation | Establish and act upon multi-year priorities | Risk Assessment (RA) | Assessment and risk mitigation | Establish and act upon multi-year priorities | Strategic Plan for FY 2024-2028 | Assessment and risk mitigation | Establish and act upon multi-year priorities | Medical Response Surge Exercise (MRSE) | Assessment and risk mitigation | Establish and act upon multi-year priorities | 0. Administrative Oversight | Recipient | 1% | 1% | In state | Commercial | Monthly | Yes | Cash
Financial Administration | Jurisdiction Information | Information sharing | Enhance and sustain HCCs | Hazard Vulnerability Assessment (HVA) | Information sharing | Enhance and sustain HCCs | Readiness Plan | Information sharing | Enhance and sustain HCCs | Patient Movement Exercise | Information sharing | Enhance and sustain HCCs | 0.1 Program Administration | Health care coalition | 2% | 2% | Out of state | Health care coalition | Quarterly | No | In-kind contributions
Sub-recipient Monitoring and Management |  | Specialty care planning and coordination | Coordination | Readiness Assessment | Specialty care planning and coordination | Coordination | Training and Exercise Plan | Specialty care planning and coordination | Coordination | Federal Patient Movement Exercise | Specialty care planning and coordination | Coordination | 0.2 Financial Administration | Multiple | 3% | 3% |  | Other public entity | Semi-Annual
Program Reporting |  | Respond | Continuity of health care service delivery | Supply Chain Integrity Assessment | Respond | Continuity of health care service delivery | Response Plan: Information-Sharing Plan | Respond | Continuity of health care service delivery | Cybersecurity Exercise | Respond | Continuity of health care service delivery | 0.3 Sub-recipient Monitoring and Management | Other | 4% | 4% |  | State or local hospital association | Annual
Performance Evaluation |  | Health care workforce support |  | Workforce Assessment | Health care workforce support |  | Response Plan: Resource Management Plan | Health care workforce support |  | Non-Cyber Extended Downtime Exercise | Health care workforce support |  | 0.4 Program Reporting |  | 5% | 5% |  | Business support services
|  | Resource management |  | Cybersecurity Assessment | Resource management |  | Response Plan: Workforce Readiness / Resilience Plan | Resource management |  | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Resource management |  | 0.5 Performance Evaluation |  | 6% | 6% |  | Information Technology (IT) consulting services
|  | Training, exercise, and evaluation |  | Extended Downtime Health Care Delivery Impact Assessment | Training, exercise, and evaluation |  | Response Plan: Medical Surge Support Plan | Training, exercise, and evaluation |  | Statewide Exercise | Training, exercise, and evaluation |  | 1. Establish governance |  | 7% | 7% |  | Private laboratory (non-university affiliated)
|  | Continuity and recovery |  |  | Continuity and recovery |  | Response Plan: Patient Movement Plan | Continuity and recovery |  |  | Continuity and recovery |  | 1.1 HCC Governance Document |  | 8% | 8% |  | Security services
|  | Organizational development |  |  | Organizational development |  | Response Plan: Allocation of Scarce Resources Plan | Organizational development |  |  | Organizational development |  | 1.2 Jurisdiction Information |  | 9% | 9% |  | Temporary staff agency
[7 empty] | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | [5 empty] | 2. Assess readiness |  | 10% | 10% |  | Inter-agency department/division
[7 empty] | Continuity and Recovery Plan: Cybersecurity Support Plan | [5 empty] | 2.1 Risk Assessment (RA) |  | 11% | 11% |  | Local public health department / agency
[7 empty] | Continuity and Recovery Plan: Extended Downtime Support Plan | [5 empty] | 2.2 Hazard Vulnerability Assessment (HVA) |  | 12% | 12% |  | National or federal government agency
[7 empty] | Continuity and Recovery Plan: Recovery Plan | [5 empty] | 2.3 Readiness Assessment |  | 13% | 13% |  | Public health laboratory
[13 empty] | 2.4 Supply Chain Integrity Assessment |  | 14% | 14% |  | Tribal entities / government
[13 empty] | 2.5 Workforce Assessment |  | 15% | 15% |  | Other local government agencies
[13 empty] | 2.6 Cybersecurity Assessment |  | 16% | 16% |  | Other state government agencies
[13 empty] | 2.7 Extended Downtime Health Care Delivery Impact Assessment |  | 17% | 17% |  | Police, fire, HAZMAT, or emergency medical services
[13 empty] | 3. Plan and implement |  | 18% | 18% |  | Local schools, educational institutions, and school boards
[13 empty] | 3.1 Strategic Plan for FY 2024-2028 |  | 19% | 19% |  | Health care facilities and networks - Inpatient
[13 empty] | 3.2 Readiness Plan |  | 20% | 20% |  | Poison Control Center
[13 empty] | 3.2.1 Training and Exercise Plan |  | 21% | 21% |  | Health care facilities and networks – Outpatient
[13 empty] | 3.3 Response Plan |  | 22% | 22% |  | University (both public and private institutions)
[13 empty] | 3.3.1 Information-Sharing Plan |  | 23% | 23% |  | Faith-based organization
[13 empty] | 3.3.2 Resource Management Plan |  | 24% | 24% |  | Private non-profit organization
[13 empty] | 3.3.3 Workforce Readiness / Resilience Plan |  | 25% | 25% |  | Contracts – Other
[13 empty] | 3.3.4 Medical Surge Support Plan |  | 26% | 26%
[13 empty] | 3.3.5 Patient Movement Plan |  | 27% | 27%
[13 empty] | 3.3.6 Allocation of Scarce Resources Plan |  | 28% | 28%
[13 empty] | 3.4 Continuity and Recovery Plan |  | 29% | 29%
[13 empty] | 3.4.1 Continuity of Operations Plan (COOP) |  | 30% | 30%
[13 empty] | 3.4.2 Cybersecurity Support Plan |  | 31% | 31%
[13 empty] | 3.4.3 Extended Downtime Support Plan |  | 32% | 32%
[13 empty] | 3.4.4 Recovery Plan |  | 33% | 33%
[13 empty] | 4. Exercise and Improve |  | 34% | 34%
[13 empty] | 4.1 Medical Response and Surge Exercise (MRSE) |  | 35% | 35%
[13 empty] | 4.2 Patient Movement Exercise |  | 36% | 36%
[13 empty] | 4.3 Federal Patient Movement Exercise |  | 37% | 37%
[13 empty] | 4.4 Cybersecurity Exercise |  | 38% | 38%
[13 empty] | 4.5 Non-Cyber Extended Downtime Exercise |  | 39% | 39%
[13 empty] | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement |  | 40% | 40%
[13 empty] | 4.7 Statewide Exercise |  | 41% | 41%
[15 empty] | 42% | 42%
[15 empty] | 43% | 43%
[15 empty] | 44% | 44%
[15 empty] | 45% | 45%
[15 empty] | 46% | 46%
[15 empty] | 47% | 47%
[15 empty] | 48% | 48%
[15 empty] | 49% | 49%
[15 empty] | 50% | 50%
[15 empty] | 51% | 51%
[15 empty] | 52% | 52%
[15 empty] | 53% | 53%
[15 empty] | 54% | 54%
[15 empty] | 55% | 55%
[15 empty] | 56% | 56%
[15 empty] | 57% | 57%
[15 empty] | 58% | 58%
[15 empty] | 59% | 59%
[15 empty] | 60% | 60%
[15 empty] | 61% | 61%
[15 empty] | 62% | 62%
[15 empty] | 63% | 63%
[15 empty] | 64% | 64%
[15 empty] | 65% | 65%
[15 empty] | 66% | 66%
[15 empty] | 67% | 67%
[15 empty] | 68% | 68%
[15 empty] | 69% | 69%
[15 empty] | 70% | 70%
[15 empty] | 71% | 71%
[15 empty] | 72% | 72%
[15 empty] | 73% | 73%
[15 empty] | 74% | 74%
[15 empty] | 75% | 75%
[15 empty] | 76% | 76%
[15 empty] | 77% | 77%
[15 empty] | 78% | 78%
[15 empty] | 79% | 79%
[15 empty] | 80% | 80%
[15 empty] | 81% | 81%
[15 empty] | 82% | 82%
[15 empty] | 83% | 83%
[15 empty] | 84% | 84%
[15 empty] | 85% | 85%
[15 empty] | 86% | 86%
[15 empty] | 87% | 87%
[15 empty] | 88% | 88%
[15 empty] | 89% | 89%
[15 empty] | 90% | 90%
[15 empty] | 91% | 91%
[15 empty] | 92% | 92%
[15 empty] | 93% | 93%
[15 empty] | 94% | 94%
[15 empty] | 95% | 95%
[15 empty] | 96% | 96%
[15 empty] | 97% | 97%
[15 empty] | 98% | 98%
[15 empty] | 99% | 99%
[15 empty] | 100% | 100%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tran-Kiem, Jenn @Hitchcock, Katherine @Drobac, Camila All the Data Validation options on respective tabs I relocated here to reduce user error. I suggest hiding this sheet in final version.